SafeHaven

Phase-wise implementation plan

From setup to deployment and submission · Kosi flood, Darbhanga, Bihar scenario

Meta Global AI Developer Hackathon 2026 · Indie Developer track · Build for Your World

Nitesh Pandey

B.Tech CSE (Bioinformatics), Vellore Institute of Technology

Version 1.1 · 26 October 2026

# Contents

# Document control

| Item | Detail |
| --- | --- |
| Project | SafeHaven: flood safety and relief planning platform |
| Document | Phase-wise implementation plan, from setup to deployment and submission |
| Companion document | SafeHaven Product, HLD and LLD |
| Scenario | Kosi flood, Darbhanga, Bihar, 27 September – 7 October 2024 |
| Author | Nitesh Pandey, VIT Vellore |
| Version and date | 1.1 · 26 October 2026 (scenario: Bihar) |
| Internal deadline | Wed 4 Nov 2026, 9:00 PM IST |
| Hard deadline | Thu 5 Nov 2026, 7:30 AM IST (4 Nov, 9:00 PM ET) |

# 1. Overview

This plan takes SafeHaven from an empty repository to a deployed, submitted hackathon entry in ten days. It replays the Kosi flood of September–October 2024 in Darbhanga, Bihar, when the Birpur barrage released its highest discharge in 56 years and the Kosi breached its embankment near Kiratpur, and follows the design in the Product, HLD and LLD document.

| Item | Detail |
| --- | --- |
| Zone | Kiratpur and Ghanshyampur blocks, Darbhanga district (~15 × 15 km); UTM 45N (EPSG:32645) |
| Replay window | 27 September – 7 October 2024; embankment breach near Kiratpur on 29–30 September |
| Users | Flood victims (citizen app); authorities, rescue teams, NGOs and food-security groups (console) |
| Meta models | SAM 3.1 (vision), Muse Spark (agents), Glimmer (offline edge node) |
| Languages | Hindi, Maithili, English |
| Emergency number | 112 (India emergency response), shown in every citizen answer |
| Track and theme | Indie Developer track; Build for Your World |

## 1.1 Build principles

- Core first. Risk, routing and camp siting must work before any AI feature is added.

- Code decides; models perceive and communicate. No model chooses a route, a camp or a rescue priority.

- Every feature has a fallback. If a model or the network fails, a simpler path still works.

- Prove it with numbers. Each measurable phase produces one metric for the write-up.

- Deploy early. A live URL exists from Day 2, so deployment is never a last-day surprise.

## 1.2 Schedule at a glance

| Phase | Day and date | Focus | Exit criterion |
| --- | --- | --- | --- |
| 0 | Day 0 · Mon 26 Oct | Setup and de-risking | Every model call works; decisions recorded |
| 1 | Day 1 · Tue 27 Oct | Data foundation | All layers align in QGIS |
| 2 | Day 2 · Wed 28 Oct | Risk engine and breach simulation | Replay shows water spreading from the breach |
| 3 | Day 3 · Thu 29 Oct | Routing and planning core | Gate 1: /route < 1 s; /console/plan returns sites |
| 4 | Day 4 · Fri 30 Oct | Citizen app | Route works end to end on a phone |
| 5 | Day 5 · Sat 31 Oct | Vision (SAM 3.1) | Photo reroutes a route; drone frame creates a rescue candidate |
| 6 | Day 6 · Sun 1 Nov | Agents and channels | 20 inputs per language pass or fall back |
| 7 | Day 7 · Mon 2 Nov | Authority console | Official plans camps and assigns a rescue |
| 8 | Day 8 · Tue 3 Nov | Offline, edge node, replay, deployment | Gate 2 (feature freeze): all demo scenes run live |
| 9 | Day 9 · Wed 4 Nov | Prove and ship | Submitted by 9 PM IST |

Gate rule: if a gate is missed by more than half a day, apply the cut list in Section 12 immediately rather than working later into the night. Plan for 8–10 focused hours a day.

# 2. Phase 0: Setup and de-risking (Day 0, Mon 26 Oct)

Goal: confirm every external dependency works before building on it.

### Tasks

- Repository. Create safehaven with folders pipeline/, engine/, api/, llm/, web/citizen, web/console, web/shared, tests/, data/ (raw and processed, git-ignored).

- Python environment. Conda from conda-forge: geopandas osmnx rasterio pysheds networkx shapely fastapi uvicorn sqlalchemy pydantic pytest. Node 20 for the frontends. Install QGIS for visual checks.

- Secrets. Model API key in .env; commit .env.example; add .env to .gitignore.

- Muse Spark checks. One call in Hindi, one in Maithili (check quality with a native speaker), and one with a tool definition to confirm whether tool calling works.

- SAM 3.1 check. One call on a flood photo with prompts water, person, cow, roof; confirm the mask format and latency.

- Glimmer. Decide where it runs: your laptop (check RAM and GPU) or a hosted partner using Modal or Baseten credits.

- WhatsApp (optional). Try the Cloud API test number; drop it if it is not working within 2 hours.

- Footage. Start collecting openly licensed Kosi 2024 flood photos and drone clips from Bihar; record the licence for each.

- Kickoff and rules. Join the kickoff livestream (10:30 PM IST); read the Official Rules; list the required submission fields.

Deliverables: working repo and environment; DECISIONS.md recording tool calling yes/no, Maithili yes/no, Glimmer host, WhatsApp yes/no.

Exit criterion: each model call succeeds.

If it goes wrong: no tool calling → plan JSON-mode outputs executed by the backend; weak Maithili → Hindi carries the assistant and Maithili moves to the cut list.

# 3. Phase 1: Data foundation (Day 1, Tue 27 Oct)

Goal: every map layer for the zone, aligned in one coordinate system and visually checked.

### Tasks

- Zone. Draw the polygon around Kiratpur and Ghanshyampur blocks at geojson.io; save zone.geojson. Process everything in EPSG:32645; convert to EPSG:4326 only for the web.

- Roads. osmnx.graph_from_polygon(zone, network_type="walk") and "drive"; save GraphML. Rural Bihar is thinly mapped, so check coverage in QGIS and add obvious missing village tracks by hand.

- Buildings. Add Google Open Buildings footprints to find villages and candidate shelters OSM misses.

- Sites. Schools, panchayat and public buildings, primary health centres, flood shelters and embankment tops (trace the embankment line from OSM man_made=dyke or by hand). Mark official relief centres from Darbhanga district administration or Bihar SDMA notices where available.

- Terrain. Copernicus GLO-30 DEM with a 5 km buffer; reproject; compute HAND with pysheds (fill pits, fill depressions, resolve flats, D8 flow, accumulation, stream threshold tuned to the Kosi channels and local rivers); compute depression depth (filled DEM − DEM), which picks out low fields and chaurs. Time-box HAND to 4 hours.

- Population. WorldPop India 100 m, clipped and resampled to the 30 m grid (sum-preserving).

- River and rain. Open-Meteo hourly rainfall and river discharge for 27 September – 7 October 2024; transcribe daily Kosi water levels, danger levels and Birpur barrage discharge from Bihar Water Resources Department flood bulletins into river_daily.csv.

- Breach point. Record the breach location near Kiratpur and its time window from news reports; save breach.geojson, along with the embankment line.

- Validation list. 15–20 villages reported flooded after the 29–30 September 2024 breach, with coordinates and sources.

Deliverables: data/processed/ containing walk and drive graphs, sites.geojson, dem.tif, hand.tif, depr.tif, pop.tif, rain_hourly.nc, river_daily.csv, breach.geojson, validation.csv.

Exit criterion: all layers line up in QGIS; low HAND follows the Kosi channels; validation villages sit in low-lying areas.

If it goes wrong: HAND fails → use elevation plus distance to river as susceptibility; WRD bulletins hard to read → use Open-Meteo discharge alone.

# 4. Phase 2: Risk engine and breach simulation (Day 2, Wed 28 Oct)

Goal: an hour-by-hour flood picture for the replay window that matches what happened.

### Tasks

- Static susceptibility in engine/risk.py: S = 0.6 × clip(1 − HAND/10 m) + 0.4 × clip(depression/1.5 m).

- River forcing: interpolate daily Kosi levels to hourly; R_river = clip((level − warning) / (danger − warning)); R24 = max(R_rain, R_river). Birpur barrage releases lead downstream levels by hours to a day; use them for the forecast layer.

- Breach simulation (about 5 hours): start at the breach cell at the recorded breach time; set the water level at the breach from the river level in the bulletin; each hour expand a priority queue (lowest ground first) into neighbouring cells below the water level minus a head loss per kilometre from the breach; cap cells added per hour so water advances over hours; output an hourly F_breach mask with risk ≥ 0.9 inside it.

- Combine: risk = min(1, w1·S·(1 + w2·R24) + w3·max(F_obs, F_breach) + w4·C), with all weights in engine/config.py.

- Precompute hourly risk rasters, edge risks for both graphs (maximum of samples every 20 m along each edge), and PNG risk tiles.

- Validate: share of validation villages inside high-risk cells at peak; tune head loss and spread rate.

- Deploy a hello-world API to Render or Railway to prove the deployment pipeline early.

# engine/risk.py (outline)

def breach_mask(hour, dem, breach, river_level, head_loss, max_cells, prev_mask):

if hour < breach.start_hour:

return empty_mask()

level = river_level(hour)                         # from WRD bulletins

queue = frontier_of(prev_mask) or [breach.cell]   # lowest ground first

added = 0

while queue and added < max_cells:

cell = queue.pop()

if dem[cell] < level - head_loss * dist_km(cell, breach.cell):

mark_flooded(cell); push_neighbours(queue, cell); added += 1

return flooded_mask

Deliverables: risk/, edges/, tiles/ folders for every hour; validation_report.md with the first number.

Exit criterion: stepping through the hours shows water spreading from the breach into villages; most validation villages end up flooded.

If it goes wrong: spread model misbehaves → a simple distance-and-elevation mask that grows from the breach each hour; keep the visual story.

# 5. Phase 3: Routing and planning core (Day 3, Thu 29 Oct)

Goal: the decision logic works behind an API.

### Tasks

- Routing in engine/routing.py: edge cost length × (1 + 10 × risk); remove edges above 0.7 (walk) or 0.4 (vehicle); KD-tree snap; one Dijkstra to all eligible shelters; rank by cost and shelter score; return top 3.

- Needs: mobility removes steps edges and caps distance at 1.5 km; medical boosts health centres.

- Fallback: if nothing is reachable, return the highest reachable point within 1 km (often the embankment) plus "move to higher ground and call 112".

- Camp siting in engine/siting.py: demand = population in cells with risk ≥ 0.5 now or in the next 12 hours, clustered at ~150 m; candidates = low risk for 24 hours and truck-reachable; coverage by flood-aware Dijkstra up to 2 km; greedy maximal coverage for k sites.

- Food points: capacity-aware variant; demand per site × ration rate set by the NGO.

- Database: SQLite in WAL mode with tables sites, reports, rescue_requests, media, blocked_edges, plans, alerts, snapshots, users.

- Endpoints: /route, /sites, /risk-tiles, /reports, /rescue, /snapshot/latest, /console/plan, /health.

- Tests: route-safety test (no edge above threshold) and siting sanity test in pytest; GitHub Actions running on every push.

Exit criterion: Gate 1: /route responds in under 1 second; /console/plan returns ranked sites with people covered; tests green.

If it goes wrong: siting slow → fewer demand clusters or candidates; capacity variant moves to the cut list.

# 6. Phase 4: Citizen app (Day 4, Fri 30 Oct)

Goal: a person on a phone can find a safe place and a route.

### Tasks

- Scaffold web/citizen with Vite, React and react-leaflet; shared map components and API client in web/shared.

- Location: browser Geolocation (needs HTTPS and permission); fallbacks: tap a pin, search, or type a landmark; out-of-zone message.

- Home screen: full-screen map, large "Find safe spot" and "I need rescue" buttons, network badge, language toggle.

- Result card: shelter name, "official" or "possible high ground" label, distance, walking time, road to avoid, link to open in Google Maps.

- Rescue request: location, number of people, needs (elderly, children, medical), optional phone number.

- Report form: photo, location, note; depth picker shown only if SAM finds no reference object (wired in Phase 5).

- Language: Hindi interface by default, English toggle; Maithili strings if Phase 0 confirmed quality.

- Design for stress and low-end phones: 48 px touch targets, high contrast, short text.

Exit criterion: on a real phone, tap a location in the replay and see a route on the map.

# 7. Phase 5: Vision with SAM 3.1 (Day 5, Sat 31 Oct)

Goal: photos and video become flood data that changes routes and creates rescue alerts.

### Tasks

- Client in engine/vision.py: resize to 1024 px; strip EXIF except GPS and time; call SAM 3.1 with text prompts; keep masks above 0.5 confidence.

- Rural depth estimator using the reference objects in the table below; map the submerged fraction to ankle, knee, waist or above.

- Report effects: structured level and confidence raise risk within 100 m, decaying over 6 hours; duplicates within 50 m and 30 minutes merge.

- Video road flooding: 1 frame per second, max 60 frames; segment road and water; block an edge when water covers more than 60% of the road mask for 3 consecutive frames.

- Stranded detection: a person mask on a roof mask with water nearby creates a rescue candidate with an image crop, marked unconfirmed.

- Evaluation: hand-label 30 photos (ankle, knee, waist, above); compute exact and within-one-level accuracy; label 20 aerial frames for detection precision and recall.

- Demo gallery: 6–8 sample photos and one clip built into Demo mode.

| Reference object | Height | Knee threshold | Waist threshold |
| --- | --- | --- | --- |
| Standing person | 1.65 m | 10–30% submerged | 30–60% |
| Cow (shoulder) | ~1.4 m | 15–35% | 35–60% |
| Hand pump | ~1.0 m | 25–50% | 50–80% |
| Door | 2.1 m | 7–25% | 25–50% |

Exit criterion: submitting a photo reroutes a nearby route; a drone frame creates a rescue candidate; evaluation numbers recorded.

If it goes wrong: depth estimator noisy → keep coarse levels and show confidence; no usable drone footage → use still aerial images, clearly labelled.

# 8. Phase 6: Agents and channels (Day 6, Sun 1 Nov)

Goal: people and officials can talk to SafeHaven in their own words.

### Tasks

- Client in llm/client.py: Model API through the OpenAI-compatible SDK; 15-second timeout; one retry.

- Shared tools in llm/tools.py: find_safe_route, geocode_landmark, submit_report, request_rescue, get_shelter_status; copilot-only query_reports, coverage_gaps, recommend_sites, rank_rescue_queue, draft_sitrep, draft_alert.

- Citizen assistant prompt: reply in the user's language and script; at most 3 sentences; always use a tool for locations; never invent places; include 112 and the state disaster helpline; one clarifying question if location is unknown.

- Copilot prompt: numbers only from tool results; recommendations labelled as such; alerts are drafts for human approval.

- Validators: Pydantic schemas on every tool call and answer; place-name check against tool results; at most 4 tool calls per turn; fallback to buttons and template text.

- Channels: SMS-style text box (/sms/inbound, one SMS-length reply); WhatsApp test number if Phase 0 succeeded.

- Testing: 20 inputs per language (Hindi, Maithili, English), including typos and mixed Hindi-English; log every result.

Exit criterion: every test input either succeeds or falls back cleanly; one Maithili or Hindi exchange works well enough for the video.

If it goes wrong: no tool calling → JSON-mode output parsed and executed by the backend.

# 9. Phase 7: Authority console (Day 7, Mon 2 Nov)

Goal: officials, rescue teams and NGOs see one live picture and act on it.

### Tasks

- Scaffold web/console reusing shared map components; login with seeded accounts and roles (authority, rescue, NGO, camp manager); read-only judge account.

- Situation map: layers for risk, breach extent, reports by level, rescue requests, camps, blocked roads, uncovered clusters; time slider.

- Report feed: photo, SAM level, confidence, merged duplicates.

- Rescue queue: priority = people × severity × vulnerability × waiting time; confirm, assign team (including boats), close; evidence thumbnails for SAM candidates.

- Planning screen: kind (camp or food point), k, maximum distance; map of recommended sites with coverage; people covered and uncovered clusters; lock a site and recompute.

- Video upload: progress, frames with masks, edges blocked, candidates created.

- Copilot panel and live updates via Server-Sent Events (/events), with polling fallback on weak networks.

Exit criterion: an official runs camp siting, sees a new photo report appear live, and assigns a rescue team.

If it goes wrong: SSE trouble → 15-second polling; food planner and alerts move to the cut list.

# 10. Phase 8: Offline, edge node, replay and deployment (Day 8, Tue 3 Nov)

Goal: everything works on the live URL, including with no network.

### Tasks

- Snapshot: gzip JSON with nodes, edges (length, risk as 0–255, flags), sites, thresholds, version and hash; target 2–4 MB; delta updates by version.

- Offline map: build a PMTiles file for the zone (Protomaps) and serve it from your own hosting.

- Service worker (Workbox): cache-first for app shell, map and snapshot; network-first with 3-second timeout for API calls.

- On-device routing: port the cost function to JavaScript (ngraph.path) with a stricter offline threshold (0.5) and a data-age label; parity test against the server on 50 origins.

- Queued writes: reports and rescue requests in IndexedDB, sent by Background Sync with client UUIDs for de-duplication.

- Glimmer edge node: run the API image in edge mode on your laptop with Glimmer; phones on its Wi-Fi get chat and routes with no internet.

- Demo mode: default landing with replay slider and "Replay of the Kosi flood, Sep–Oct 2024" label; sample photo gallery; judge login shown.

- Deployment: follow Section 10.1.

- User tests: five people from Bihar, ideally from Darbhanga or other Kosi-region districts, find a shelter from their own village in the replay; collect one quote; try for one relief NGO or Bihar SDMA contact.

- Rehearse every demo scene on the live URL on two phones.

## 10.1 Deployment steps

| Step | Component | Action | Check |
| --- | --- | --- | --- |
| 1 | Data bundle | Package processed files only (graphs, edge risks, tiles, snapshots, sites); raw DEM and footage stay out | Bundle size noted; under hosting limits |
| 2 | API image | Dockerfile: Python slim base, install dependencies, copy api/, engine/, llm/ and the data bundle; uvicorn api.main:app | docker run locally; /health returns 200 |
| 3 | API hosting | Deploy the image to Render or Railway with a persistent disk for SQLite; set environment variables (Model API key, allowed origins, JWT secret) | Public /health and /docs load |
| 4 | Frontends | Connect web/citizen and web/console to Vercel; set VITE_API_URL; include PMTiles and snapshot as static assets | Both URLs load on mobile data over HTTPS |
| 5 | CORS and auth | Allow only the two frontend origins; seed demo and judge accounts | Console login works; other origins rejected |
| 6 | Keep-alive | Scheduled ping to /health every 10 minutes, or one month of the cheapest paid tier through 9 Nov | No cold start on first request |
| 7 | Monitoring | Uptime monitor on API and both frontends; log Model API errors and spend | Alert reaches your phone |
| 8 | Smoke test | Run all demo scenes on two phones on mobile data, including airplane mode | Every scene passes twice in a row |
| 9 | Rollback | Tag the release (v1.0-submission); keep the previous deploy available to restore | Restore tested once |

Exit criterion: Gate 2 (feature freeze): all demo scenes run on the live URL, including airplane mode.

# 11. Phase 9: Prove and ship (Day 9, Wed 4 Nov)

Goal: a submitted entry with evidence, a strong video and nothing broken.

### Tasks

- Fixes only. No new features after Gate 2.

- Metrics run against the targets in the table below; record results in the README.

- Video (under 3 minutes, captioned): hook with Kosi footage; breach replay with a route change; photo to depth; drone frame to rescue queue; camp siting with people covered; Maithili or Hindi assistant; airplane mode; close with metrics and a user quote. Record each scene separately.

- README: pitch, screenshots, live links, judge login, architecture diagram, how each Meta model is used, guardrails, data sources and licences, setup steps, limitations.

- Write-up: problem, users, solution, Meta tooling, metrics, comparison with existing tools, roadmap.

- Submit on the Cerebral Valley portal by 9 PM IST, Indie track, theme Build for Your World.

| Metric | Target |
| --- | --- |
| Route-safety violations at peak | 0 |
| Server/device route parity | 50 of 50 identical |
| Validation villages inside modelled flood | Report the share |
| SAM depth accuracy (30 photos) | ≥ 70% exact; ≥ 95% within one level |
| /route latency (p95) | < 1 s |

Exit criterion: submission confirmation received about 10 hours before the hard deadline.

# 12. Cut list and daily rhythm

## 12.1 Cut list (drop from the top when a gate is missed)

- Glimmer edge node (keep on-device routing with template text).

- WhatsApp channel (keep the SMS-style text box).

- Broadcast alerts and camp-manager updates.

- Food-point capacity planner (keep camp siting).

- Maithili (keep Hindi and English).

- Video road flooding (keep photo depth and stranded detection from stills).

Never cut: citizen routing, breach replay, camp siting, one SAM 3.1 feature and one Muse Spark feature on screen, the airplane-mode scene, the live URL, the video.

## 12.2 Daily rhythm

- Morning: re-read today's phase and exit criterion; check Model API spend.

- Midday: push working code; deploy if anything user-facing changed.

- Evening: commit, push, and write a two-line entry in BUILDLOG.md (it becomes the write-up).

- Before sleeping: note the first task for tomorrow.

# 13. Submission and post-submission checklists

## 13.1 Submission

| Done | Item |
| --- | --- |
| ☐ | Official Rules accepted; required submission fields filled |
| ☐ | Live URL works on mobile data; Demo mode is the default |
| ☐ | Judge login works and is listed in the submission |
| ☐ | Video under 3 minutes, captioned, uploaded |
| ☐ | Public repo with README; no keys committed; .env.example present |
| ☐ | Write-up with metrics, user quote and limitations |
| ☐ | Credits: OpenStreetMap contributors, Copernicus, WorldPop, Open-Meteo, Bihar Water Resources Department, Google Open Buildings, footage sources |
| ☐ | Replay data labelled as a past event |

## 13.2 After submission (5–9 Nov)

| Done | Item |
| --- | --- |
| ☐ | API kept awake through judging (5–8 Nov); uptime monitor on |
| ☐ | Credits and logs checked daily |
| ☐ | Two-minute live demo rehearsed for finals on 9 Nov |
| ☐ | Answers ready for likely judge questions: data freshness, who operates it, cost per district, how villagers get the app before a flood |